# Extension of Time and Loss & Expense Narrative #: section 278 delays and changes

# A. Introduction

- This narrative sets out the Contractor’s (ULS) entitlement arising out of delays to and changes in the section 278 agreement and works.

- These delays constituted Relevant Events under clause 2.26.6 and/or 2.26.13 and Relevant Matters under clause 4.21.5 respectively.

- The changes were Changes under Article 8.2 and/or clause 5.1 of the Contract and constituted Relevant Events under clause 2.26.1 and Relevant Matters under clause 4.21.1.

# B. Summary

- The Employer (THDM) was responsible for obtaining the Section 278 Agreement. There was a delay of a year in signing the Section 278 Agreement. This caused delays to ULS’ works, in particular it delayed the commencement of the necessary highway works.

- The Section 278 Agreement [Were the changes made by/in the s.278 agreement? Or did the changes come as part of the technical approvals process after? Or did the changes pre-cede the s.278?] further gave rise to changes to the works required. These were Changes

# C. Position under the Contract

- Under the Employer’s Requirements, specifically item 71 of the Schedule of Employer’s Accepted Items (SEAIs), THDM was responsible for obtaining and signing the Section 278 Agreement:

“The Employer will be responsible for all… Section Agreements (106, 278 etc) -the Contractor will have no commercial or programme responsibility in respect of these section agreements. We have allowed to assist the Employer with the provision of supporting documentation where appropriate in the resolution of the above matters.”

- ULS bore no programme or commercial risk for the Section 278 Agreement. ULS’s only obligation was to assist in providing supporting documentation where necessary.

- THDM confirmed that it was responsible for obtaining the Section 278 Agreement in the email from Jake Whiterod on 29 August 2022:

“RA are in agreement that the Employer retained responsibility for agreeing as part of its s106 the s278 for the sitewide works (encompass more than Welbourne), albeit the contractor is required where necessary to provide supporting information.”

- Under the Contract, the Section 278 Agreement was required to be signed, and the technical approval for the s.278 works, by July 2022. [Have we been able to confirm where this date came from? Or any contractual date? Will’s email of 17 November 2024 suggested a date of August 2021, but that was for a Highways Works Agreement)]

# D. Delay

## (i) Agreement of s.278

- As set out above, the Section 278 Agreement should have been signed (at the latest) by July 2022.

- The Section 278 Agreement was not in fact signed until 6 July 2023.

- This was a delay of a year.

[Can we add detail as to how THDM caused the delay? A potential issue is if THDM says the delay was caused by the Council, not them]

## (ii) Technical  approval

- By Change Notice 01, ULS was instructed to take over the technical submittals for the s.278 works. [Is this right? Was there a formal instruction or are we referring to ULS’s CN 01 29 March 2023 in which it said it would take over? Was there a letter from Calfordseaden/ THDM which CN 01 responded too?]

- In an attempt to mitigate any delays, ULS commenced with the s.278 technical submittals in [March/April. Please confirm which?] 2023, before the Section 278 Agreement was signed.

- When the Section 278 Agreement was finally signed in July 2023.

- On 11 July 2023, ULS received the signed Section 278 Agreement from Calfordseaden.

- There were a number of changes (and set out below) which necessitated changes to the technical submittals. [Is this right? Or was the technical approvals on a separate track/path, unrelated to the formal s.278 agreement?. The email on 30 June 2023 from TPS in the Key correspondence excel suggests separate discussions were ongoing on the technical approvals regardless of the s.278.]

- Havering Council provided its technical approval (albeit with 5 points of clarification) on 24 November 2023.

- ULS then had to obtain the licence under section 50 of the New Roads and Street Works Act 1991 (Section 50 Licence) to carry out the works, which it obtained on 5 December 2023.

- The section 278 works crossed into land which Transport for London (TFL) is responsible for. Technical approval was therefore required from TFL too. On 27 November 2023, TFL provided its approval. [The TFL emails on 30 January 2024 then suggest there is no approval. DO we understand why? What happened?] [There is a later TFL approval in April 2024 for tree species. Is that relevant?]

- [Note: UL’s narrative deals with our provision of information under the “Responsibility for Technical Submittals” section. That is defensive/ a reply to THDM’s defence. I don’t think we should deal with it up front]

(iii) Additional s.278 works

[The UL narrative also refers to “Additional Works – Changes from S278 Agreement”. Have the direct costs for these changes been paid for? Are these changes separate causes of delay?]

[Are we able to specify the changes, both the documents which made the changes and what the changes were? Are the changes just those in “Letter 10 s278 Changes Attachment”? If so, my reading is that they are changes AFTER the s.278 works required as part of the technical approvals]

[Is Change Request 20 relevant?]

[Is CI 20 relevant?]

# E. Legal Basis of the Claim

- The delay to the agreement and signing of the Section 278 Agreement constituted Relevant Events and Relevant Matters under clauses 2.26.6 and 4.21.5 respectively.

- The additional s.278 works constituted a Change under clause 5.1 in that there was an alteration or modification of the design, quality or quantity of the Works. [Can we identify how it changed from parts of the ERs?]

- [As above is there an alternative claim for additional works under the section 278?]

# F. Impact of the Delays

- The delay to the agreement and signing of the Section 278 Agreement caused delays to the Works. The section 278 works could not commence until 5 December 2023, when the Section 50 Licence was obtained.

- [Can we give specifics as to the impact on the rest of the works? What was delayed and why?]

- [To include table summarising all losses claimed, including (a) any total direct cost increase, (b) total delay (split between delay to agreement and additional works if there is an alternative claim), (c) total L&E, if possible separating between prolongation, thickening, and subcontractor claims]

United Living (South) Limited

January 2025