Extension of Time and Loss & Expense Narrative #: Thames Water leak

# A. Introduction

- This narrative sets out the Contractor’s (ULS) entitlement arising out of a leak from a Thames Water (TW) pipe in the site boundary.

- The leak, and the resultant excess water on the site, was a Change under clause 5.1 of the Contract and constituted a Relevant Event under clauses 2.26.1, 2.26.7 and/or 2.26.9 and a Relevant Matter under clause 4.21.1 respectively. [Note: there are no equivalent Relevant Matter clauses to 2.26.7 (statutory undertaker) or 2.26.9 (Specified Peril)]

# B. Summary

- From September 2020 to December 2020, a leak from a TW pipe led to excess water on the site, which delayed and led to the re-sequencing of ULS’s works.

# C. Position under the Contract

- An escape of water from a pipe, including a TW pipe, was a Specified Peril under the Contract. The definition of Specified Perils in clause 6.8 was as follows:

“fire, lightning, explosion, storm, flood, escape of water from any tank, apparatus or pipe, earthquake, aircraft and other aerial devices or articles dropped therefrom, riot and civil commotion, but excluding Excepted Risks.”

- [Did the contract identify any TW pipes on the site? The Geotechnical Investigation report refers to services being mapped]

- [Was the critical path activity/sequence for the ground floor slab in a contract programme?]

# D. Chronology

- In September 2020, excess water was noticed on the site, caused by a water leak. [Did we know it was due to a leak? If so, how? Or was it a guess?]

- On around 25 September 2020, the high water levels caused by the leak were beginning to effect progress of ULS's works.

- In an attempt to mitigate the impact of the delay on programme while investigations were carried out, ULS re-sequenced its works [was the re-sequence just block C?] to commence with the upper floor levels to Block C.

- Despite frequent visits through September and October 2020 to attempt to identify the source of the leak, TW was unable to locate the source of the leak and excess water remained on the site.

- In addition to delay and disruption to ULS's works, there became concerns over the future viability of the design methodology of the ground floor slab, should the leak not be discovered and repaired by TW.

- In order to permit TW to carry out investigatory excavations, on 25 November 2020 ULS had to adapt its hoarding.

- On 27 November 2020, TW carried out its investigatory excavation but was unable to find the leak.

- On 7 December 2020, TW returned to site requesting further adaptions to the hoarding to enable further investigations.

- On 9 December 2020,  TW returned again to the site and advised that they needed to carry out works over the weekend;

- On 12 December 2020, TW undertook further excavations on site. No leak was found. TW advised that they needed to investigate another location.

- On 14/15 December 2020, TW carried out more excavation works and finally discovered the location of the leak.

- ULS notified the Client Management Team (CMT) on 15 December 2020 of TW’s discovery of the leak. CMT enquired whether the leak was on ‘new or old infrastructure’. ULS responded stating it was ‘difficult to see due to the surging water…’. CMT advised that ‘VFP are being informed’ and ‘TW should be completing the repair’. ULS advised that TW were ‘completing repairs this evening’.

- However, on 16 December 2020, ULS notified the CMT that the TW team on site had been diverted due to ‘another emergency elsewhere’ and the repair works were consequently incomplete.

- On 17 December 2020, ULS emailed the EA and CMT providing details of the leak, including a timeline of events. The email included a marked-up drawing showing the location of the leak, photos and a video.

- On 22 December 2020, 7 days after it had identified the leak, TW finally returned to site to repair the leak. [The previous narrative also said the leak was fixed on 23 Dec (as well as 22 Dec). Which date was correct?] . Footpath works were still outstanding. [when were the footpath works fixed? What were these?]

- The Christmas shutdown then started from [Please confirm when started?] to [Please confirm when ended?].

# E. Legal Basis of the Claim

- The leak  from the TW pipe, and the consequent excess water, was a Change under clause 5.1.2 in that it added to or altered obligations or restricted imposed in the Employer’s Requirements in regard to:

  - Clause 5.1.2.1 – access to the site or use of any specific parts of the site. ULS could not use or access the areas of site subject to excess water, or areas subject to TW’s excavations, to carry out the planned works in those areas.

  - Clause 5.1.2.2 – limitations of working space. ULS’s space was limited by the excess water and TW’s investigations and excavations. The latter required ULS to adjust its hoardings.

  - Clause 5.1.2.4 – the execution or completion of the work in any specific order.  ULS had to re-sequence the works re-sequenced its works to commence with the upper floor levels to Block C in September 2020 and had to delay the pouring of the ground floor slab.

- The Change amounted to a Relevant Event and Relevant Matter under clauses 2.26.1  and 4.21.1 respectively.

- The leak, and TW’s delay in and failure to identify and repair the leak, further constituted a Relevant Event under clauses 2.26.7, in that the investigations and repair works involved the carrying out and failure to carry out by TW, a statutory Undertaker, of work in pursuance to its statutory obligations to maintain and repair its pipes.

- Further or alternatively, the leak and escape of water constituted a Relevant Event under clause 2.26.9 as a “loss or damage occasioned by any Specified Peril”. An escape of water from a pipe was a Specified Peril under the Contract.

# F. Impact of the leak

- The ground floor slab [Is this a single slab for the whole site? Or a particular block?], which was on the critical path, had been due to commence on 16 September 2020, as detailed in the groundworks subcontractor’s programme.

- The pouring of the ground floor slab could not commence or progress as a result of the excess water caused by the leak or while the investigations and repairs were ongoing.

- After the leak was fixed, and after the water levels returned to normal following the Christmas shutdown, ULS was able to pour the ground floor slab on 4 January 2021. This was 16 weeks later than planned.

United Living (South) Limited

January 2025

RE_ Thames Water leak