Extension of Time and Loss & Expense Narrative #: Secured by Design

# A. Introduction

- This narrative sets out the Contractor’s (ULS) entitlement arising out of changes to the Secured by Design (SBD) requirements from the Works. SBD is a “police initiative to encourage the building industry to adopt crime prevention measures in the design of developments to assist in reducing the opportunity for crime and the fear of crime, creating a safer and more secure environment.” (SBD, 2004)

- The changes to the SBD requirements were Changes under clause 5.1 of the Contract and constituted a Relevant Event and Relevant Matter under clauses 2.26.1 and 4.21.1 respectively.

# B. Summary

- THDM changed ULS’s obligation to comply with the principles of SBD 2010 to complying with SBD 2019 and obtaining accreditation.

- These changes led to additional design and works to comply with the additional SBD requirements. [Is it a delay event?]

# C. Position under the Contract

- Under the Contract, ULS was required to comply with the principles set out in the Secured by Design 2010 “New Homes” guide (SBD 2010). See:

  - Employers Requirements Volume 1 Tender & Contractual Information; B.04 Forward Funding Agreement (p1,059 of 8,281)m General Specification Requirements, Part 1, Section 2 Compliance Standards:

"The scheme shall meet the following requirements:

b. Secured by Design principles".

  - Employers Requirements Volume 2; D.01; Architectural Information, Report; Stage 3 Outline Design Intent Specification (Page 3,850 of 8,281):

"Secured by Design New Homes 2010 – Principles not certification"

  - Employers Requirements Volume 2; D.01; Architectural Information, Report; Stage 3 Outline Design Intent Specification (p3,851 of 8,281):

"The scheme does not require Secure by Design certification but must comply with guidance provided by Hoare Lea ‘s security strategy and prepared by ESD. Any units falling below these standards should be brought to the attention of the Employer as soon as possible.”

  - Addendum 2; Site Masterplan Design and Access Statement; Section 6.6; Access Planning Policy and Guidance (page 6,784 of 8,281). The Development Management Development Plan Document (DPD), dated July 2017, addresses ‘Accessible and Safe Environments’  under Policy DM2, as follows:

"(A) Proposals should ensure that new developments:

(a) Can be used safely, easily and with dignity by all;

(b) Are designed so that the layout improves people’s access to social and community infrastructure, including local shops and public transport;

(c) Protect, improve and create, where appropriate, safe and accessible pedestrian and cycling routes and should not impede pedestrian and cycling permeability; and

(d) Have regard to the principles set out in ‘Secured by design’."

- SBD was not required, under the Contract, to obtain SBD accreditation or comply with Secured by Design Homes 2019 (SBD 2019), which only applied to new SBD applications after 1 April 2019. The concept of Bronze, silver and Gold Accreditation levels was only introduced in SBD 2019. [when was the SBD application made? Is this a separate application or should it be read as referred to the planning application?]

- Hoare Lee, the Security Consultant engaged by THDM, confirmed in an email on 17 February 2021 that:

"There will be areas within the application that aren't applicable to your development or you haven't [been] included within your design as you are only following the principles of SbD.

We have found that this then allows the DOCO to understand the development, as for some reason they are not reading reports.

Don't worry to [sic] much about the standard, as technically you are not applying for SbD certification, it's just to show the DOCO that you have included a number of the principles.".

# D. Change

- In or around July 2020, the Secured by Design officer contacted CWZG to state that the Project was required to achieve SBD accreditation in accordance with the SBD 2019 standards. CWZG responded to the SBD officer to advise that ULS is only required to work in accordance with the SBD 'principles' and not to achieve any SBD accreditation.

- In circumstances where these works were additional to those required under the Employer's Requirements,  on 9 September 2020 ULS raised  Request for Further Information ("RFI") No. 18 to seek instructions in respect of the additional SBD requirements:

“Secured by Design have requested measures to address communal compartmentation of the common areas, i.e. secure air lock & lift lobby air locks on all floors with Audio/visual access control or destination control on lift cars and secure stair cores.

• Access provision to all Lifts by Key Fob

• Access provision to all Upper Stairwell Lobbies by Key Fob

• Additional CCTV to cover the Car Park, Generator and Transformer entrances in line with SbD  (Car Park, Generator and Transformer entrances)

The above measures were not included in Stage 3 info, and it’s additional to ER.

A RFI was raised on 09/09/2020 to seek clarification, and a clear confirmation has not been provided.

This is causing delays in Patrick Parsons and LJJ Security and Access control packages progress

ULS have contacted our subcontractor to provide a high level price for the current SBD officer’s requirements. We have received a high level quotation of £105k, from the MEP contractor, before any consideration of other consultants and UL mark-up.

Please provide advise if you wish to instruct these work, or can you provide a further detail of actually what you require UL subcontractors to price under a client change request and we will arrange for this to be priced and returned."

- At a progress meeting in October 2020 ULS was instructed to "push back on any matter that is not included in the ERs", an acceptance by THDM that SBD's requests were beyond the requirements set out in the Employer’s Requirements.

- In October 2020 and November 2020 Client Contractors Report it was noted that a client instruction was required in respect of the changes requested by Secured by Design.

- In November 2020, it was also noted that THDM was in communication with the London Borough of Haringey (LBH) directly in relation to the additional requirements introduced by the SDB officer. The site meeting minutes also record that "ULS have requested an instruction relating to SBD. TB has provided LBH with a list of the additional SBD requirements. LBH to consider and respond accordingly".

- In the absence of any further response to its request for an instruction, in January 2021 ULS issued EWN 003 to THDM highlighting the changes that were now required due to SBD's additional requirements, and further to pricing such changes with its subcontractor:

"Please can you provide confirmation for what elements you would like ULS to provide a cost for, so I can get LJJ to provide a more detail breakdown to enable the client/LBH to make an [sic] decision on whether they wish to install any additional security requirements over the contract ER requirements".

- On 29 June 2021 Calfordseaden responded to ULS’ RFI 18 and instructed ULS to carry out the additional requirements identified in RFI 18:

“Please note that LBH are not able to assist on any Secure by Design matter, therefore it remains that ULS must discharge the planning condition through negotiation with the Secure by Design Officer. It would appear that ULS will need to comply with the requirements as set out within the RFI. Please advise"

- The instruction alleged that ULS was required to comply with the additional requirements as part of a planning condition. However, this is incorrect. The relevant planning condition (C15) referred to the principles of SBD 2010, not accreditation or SBD 2019:

  - The text of Condition 15 referred to the principles: (ER Volume 1; G.02; Planning Conditions Responsibility Matrix, Plot C (p1,423 of 8,281)). [Note: the summary of condition is “Secure by Design Accreditation”]

“Prior to carrying out above ground works within Plot C (excluding demolition and works to construct the building core) details shall be submitted to, and approved in writing by the Local Planning Authority to demonstrate that the Plot (and building(s) contained therein) has incorporated the principles and practices of Secured by Design where these can be practically achieved.

Where the principles cannot be achieved, then justification for this will be required. The development within Plot C shall be implemented in accordance with the approved details.”

  - The planning application (HGY/2018/2223) was submitted on 30 July 2018 and approved on 27 March 2019. SBD 2019 is only “applicable to all new SBD applications made after 1st April 2019.” [As above. When was the app made? Is it referring to the planning app? Or a specific SBD app?]

  - Quod, THDM’s planning consultant, confirmed in an email on 7 May 2011 that “the condition doesn’t require us to achieve SBD certification”.

- ULS responded to the instruction to comply with the requirements in RFI 18 and confirmed it would incur additional cost in complying which would amount to a variation:

"Many thanks for clarify this position. UL will now ask LJJ to develop up what the SBD officer has requested, which is now likely to incur additional cost as we will be treating this as a variation. The original statement from LJJ was this is going to be a '6 figure' sum".

## Comparison between SBD 2010 and SBD 2019

- The Changes between SBD 2010 and SBD 2019) are significant and include the following:

  - Access Control;

    - SBD 2010; required access control with audio visual verification or a concierge system

    - SBD 2019; Mandates live audio visual communication and remote operation for all main entrances, compartmentalised landings/entrances and storage.

  - Compartmentalisation;

    - SBD 2010; no specific requirements

    - SBD 2019; Mandates compartmentalisation requiring tailored access control systems at each core or floor level

  - Door Monitoring and Software Upgrade

    - SBD 2010; Focused on basic access control systems at entry points, with no mention of software for centralised monitoring or multi-block coordination.

    - SBD 2019; Mandates centralised monitoring software capable of real-time tracking, detailed event logs, and user management for larger developments.

  - Telephone and Internet Protocol (IP) Based Visitor Door Entry Systems;

    - SBD 2010; no specific requirements

    - SBD 2019; Requires IP-based systems capable of remote unlocking, integration with mobile devices.

  - Mag locks to communal corridors;

    - SBD 2010;  focused on physical door robustness (PAS 24 compliance) and did not mandate electronic or magnetic locks in communal corridors.

    - SBD 2019; expand on the requirements by mandating integrated use of magnetic locks for both main entrances and additional internal doorsets, ensuring alignment with security compartmentalisation strategies.

  - Doors – Physical Security;

    - SBD 2010; Entrance doorsets must be certificated to PAS 24:2007

    - SBD 2019; Entrance doorsets must be certificated to PAS 24:2016

  - Cycle storage – Physical Security;

    - SBD 2010;  No requirement for access control to storage areas, such as

    - SBD 2019; Doors providing access to communal areas, including storage, shall also be controlled via an access control system.

# E. Legal Basis of the Claim

- The instruction to accelerate the Health Centre was a Change under clause 5.1 as there were changes in the Employer’s Requirements, from compliance with SBD 2010 principles to complying with SBD 2019 and obtaining accreditation, which made necessary the alteration or modification of the design, quality or quantity of the works, including:

  - Clause 5.1.1 – the addition or substitution of any work; and/or

  - Clause 5.1.2 – the alteration of the kind or standard of any of the materials or goods to be used in the Works.

- The Change amounts to a Relevant Event and Relevant Matter under clauses 2.26.1 and 4.21.1 respectively.

- [Is there a basis to say that this was an impediment?]

# F. Impact of the Change

- In order to obtain SBD 2019 accreditation [was this in fact achieved?] ULS was ultimately required to carry out the following additional work: [which of the 3 items in RFI 18 do each of these fall under? It is not clear to me that they fall under the 3 specific bullets, but they could be part of the more general measures to address communal compartmentation/ secure air lock & lift lobby]

  - New Video Entry and Access Control: Supply and installation of additional video entrance panels, interfaces, relays and with proximity readers on every separate core level of Blocks A, B, and C.

  - Additional Data Requirements: Supply and Installation of additional data requirements, as follows:

    - Security LAN & WAN Network (includes the DA in stair cores floor 1 upwards)

    - PoE switches to Block A, B & C

    - 225m of Cat 6 patch leads

    - Additional 52 data points to Block A, B & C

  - Additional Powersupplies: Supply and installation of additional 26nr powersupplies, wiring, breakers additional surface conduit

  - Additional Access Controllers: Supply and installation of extra access controllers within the risers, each requiring a 240v unswitched spur unit and additional POE switchers for full system integration.

  - Mag Locks to all Main Communal Corridors: Supply and installation of Mag Locks to all main communal corridors, as follows:

    - Block A – 6 Mag locks

    - Block B – 15 Mag locks

    - Block C – 5 Mag locks

    - Core – 9 Mag locks (3 per core)

  - Door Monitoring and Software Upgrade: The door monitoring software was upgraded to accommodate the separate control of the system for Blocks A, B, and C, as per the ESD schematic.

  - Enhanced physical security to Bin stores, Cycle Stores and Flat Entrance doors.

- [Did SBD cause delay?]

- [Do we have itemised quantum for SBD (direct/ delay/ thickening etc)?]

United Living (South) Limited

January 2025

Addendum 2; Site Masterplan Design and Access Statement; Section 6.6; Access Planning Policy and Guidance – Page 6,784 of 8,281