Extension of Time and Loss & Expense Narrative #: CMT

# A. Introduction

- This narrative sets out the Contractor’s (ULS) entitlement arising out of actions of the Client Management Team (CMT) in its review and approval of ULS’s design documents.

- The excessive and/or wrongful comments and/or rejections of documents by the CMT constituted a Change under clause 5.1, Relevant Events under clauses 2.26.1 and/or 2.26.7 and Relevant Matters under clauses 4.21.1 and/or 4.21.5 respectively.

# B. Summary

- The CMT raised an excessive number of and/or incorrect comments on ULS’s drawings, outside of its design review role and the Employer’s Requirements, and returned an excessive and incorrect number of documents Status C, which meant the documents were not approved and ULS could not proceed with manufacture, procurement or construction.

- The comments and/or non-approvals by the CMT led to significant additional design work by ULS and caused delay.

# C. Position under the Contract

- The Contract contained an approval regime for design documents produced by ULS. This regime was set out at section 155A of B.01 of Volume 1 of the Employer’s Requirements:

“• Approval of Main Contract Design:

- The Employer`s Retained Team (ERT) [When we say “CMT” is that the ERT?] will inspect the design information in respect of compliance with the Tender documents and Contractors Submission. The ERT will respond in accordance with the drawing / design information issue and review protocol noted above. [Do we have the review protocol?]

- If drawings are returned B or C status, the Contractor should address comments within five days of receipt and re-submit using procedure described above. The ERT shall then respond as if the process has commenced once again.

- Should any comments/amendments made by the ERT to drawings submitted for approval be considered by the contractor to involve a variation which has not already been confirmed as a change to the Employers Requirements and/or Contractors Proposals, the Contractor shall notify the Employers Agent, following the procedure for Change Request Approval and Control included within Volume 1 – Employers Agent Procedures using the Change Request Form (CRF), without delay and in any case within seven days. The Contractor is not to proceed with ordering, fabrication or fixing until subsequently instructed. Claims for the extra cost of such work, if made after it has been carried out, may not be allowed.

- The electronic issue of the drawing issue sheet will also be used to notify the ERT of any drawings requiring urgent review. In such cases, a reasonable date required for return should be clearly stated. The ERT members will use their best endeavours to ensure the requirements are met.

- It should be noted that until drawings have reached status A, the Contractor is proceeding at risk.

- The same procedure should be adopted and managed by the Contractor for the approval of samples and tests, except that the Contractor shall submit additional samples to the Employer, as identified in the Specifications.

• Approval of Contractor Design

- The Contractor must submit completed design information via the project Extranet 'BIW'\ Asite to enable formal approval by the ERT. In reviewing the design, the following drawing status descriptions:

- STATUS A: Drawing approved for construction

- STATUS B: Drawing approved for work to proceed, subject to the incorporation of the comments marked on them before their use for construction.

- STATUS C: Drawing not approved. To be re-submitted in accordance with the comments made.

- The ERT will target a turnaround time for comments on the Contractor’s design information of no longer than 5 working days.”

- The Contract must be interpreted such – alternatively it was an implied term or an incidence of the implied term of co-operation and not to prevent or hinder completion – that the CMT would (a) return comments in a reasonable time, and (b) provide reasonable comments and approval statuses which were in accordance with the requirements of the Contract and the Employer’s Requirements.

- Further, in a design-and-build contract, the remit of the CMT was [I understand we say it was limited. But to what? What did we consider CMT’s role to be? Can we contrast that with our design team’s role? ]

# D. Change

- The CMT issued an excessive number of comments on the design documents and wrongly returned numerous design documents Status C (Not Approved/ Do Not Proceed), when they should have been approved Status A or B (Approved/ Proceed).

- [Ideally I would like to include: (a) some quantitative stats on the number of comments/ no. of Status C documents, and (b) a few qualitative examples of particularly poor comments/ status C documents]

- [Do we have a case on the CMT’s comments being slow/late? The ERs refer to a target of 5 working days]

# E. Legal Basis of the Claim

- The CMT’s excessive and/or wrong comments and returning of documents Status C were:

  - Changes under  clause 5.1.1 in that the CMT was (i) departing from the document review and approval procedure in the Employer’s Requirements, and (ii) seeking to impose substantive requirements beyond the Employer’s Requirements, and this made necessary the alteration or alteration of the design, quality or quantity of the Works. These Changes constituted Relevant Events under clause 2.26.1 and Relevant Matters under clause 4.21.1 respectively.

  - Relevant Events under clause 2.26.6 and Relevant Matters under clause 4.21.5 in that the wrongful and/or excessive comments and wrongful and/or excessive returning of documents Status C was an act of impediment, prevention or default by THDM or any “Employer’s Person”.

# F. Impact of the CMT’s actions

- The excessive comments from the CMT caused delays and required additional time and resource to review and address. [Please confirm?]

- The failure to approve drawings with Status A or B further prevented the manufacturing, procurement and/or construction shown on those drawings from proceedings. [Can we give a specific example? The email from Jamie Albone (“review meeting”) on 23 July 2021 refers to “it finally dawned on Charina [CMT] that block b is in delay purely based on an architectural projection whim delaying support angle and stone manafcture [sic].” Can we support/explain this?]

United Living (South) Limited

January 2025